## Sheet1
| CDC | Cradle | Loot | Putnam County | Faculty Dance | Walk Across | Dance Majors | Brooklyn Bridge | Force Continuum | MFA Dance | Horse | Pearl/D'amour
Theatre | Meany | Jones | Studio | Jones | Studio | Penthouse | Studio | SCT | Jones | Studio | Penthouse | Various
Director | Wiley | Curtis-Newton | Ryan |  |  | El-Gassier |  | Giomi | Oyetimein |  | Ramsey
Reh. Begin | 6/15 | 9/14 | 10/19 | 11/2 |  | 2/1 |  | 1/26 | 3/7 |  | 3/28 | 5/2
Load-in | 10/12 | 10/5 | 11/2 | 1/4 |  |  |  |  | 4/4 |  | 4/26
1st Tech |  | 10/19 | 11/23 | 1/19 |  |  |  |  | 4/18
Previews |  | 10/28 & 10/29 | 12/2 & 12/3 | 1/27 & 1/28 |  |  |  |  | 4/27 & 4/28
Performance |  | 10/30 - 11/8 | 12/4 - 12/13 | 1/29 - 2/7 |  |  |  |  | 4/29 - 5/8
Strike | 10/18 | 11/9 & 11/10 | 12/14 &12/15 | 2/8 & 2/9 |  | 2/29 |  |  | 5/9 & 5/10
First Design Mtg*: |  | 5/4 | 6/1 | 9/8 |  | 12/7 |  | 6/1 | 12/14 |  | 3/29
First Look @ Prelims: |  | 6/2 | 9/25 | 10/26 |  | 1/11 |  | 10/12 | 1/14 |  | 3/29 | 5/2
Bidding Package Due: |  | 6/15 | 10/2 | 11/4 |  | 1/25 |  |  | 2/1 |  | 4/7
Final Designs Due |  | 7/15 | 10/16 | 11/12 |  | 2/1 |  | 11/30 | 2/22 |  | 4/15
Light Plot Preliminary | [7 empty] | 1/4
Light Plot Due | [7 empty] | 2/3
Scenery Build |  | 9/1- | 11/2** | 11/30** |  | 2/10 - 2/12 |  |  | 3/7 |  | 4/21 | 5/2
Scenery Budget |  | 4000 | 3750 |  |  | 250 |  |  | 2700 |  | 2000 | 1000
Costume Build |  | 9/14- | 11/2 | 11/16 - 1/15 | xmas | 2/8 |  |  | 3/7 | 3/14-5/6 | 4/25 | 5/9
Costume Budget |  | 4200 | 1850 |  |  | 2500 |  |  | 2000 |  | 2000 | 1500
Light Hang/Focus |  | 10/5-10/16 | 11/2 - 11/20 | 1/4 - 1/15 |  | 2/16 - 2/19 |  |  | 4/4 - 4/14 |  |  | 5/20-5/25
Light Budget |  | 1000 | 800 |  |  | 500 |  |  | 1000 |  | 500 | 500
Sound Budget |  | 450 | 50 |  |  | 150 |  |  | 50 |  | 500 | 1000
*Approx. date, may shift slightly
# begin work before break
**May be able to start earlier on some pieces