Dear Chante`:

Congratulations on being assigned as Costume Designer for the UW School of Drama's production of *Incident at Vichy.* As you know, you will be supplying the specifications and the visual representations for the design within the parameters of the budget, schedule, and the physical limitations of the theatre, staff and shop. This memo is an attempt to consolidate and distribute a bunch of production information to assist you in that endeavor.

**Production Information**

|  |
| --- |
| *Incident at Vichy*Theatre: Jones Playhouse |
| Director: Kelly Kitchens kitchenskelly@yahoo.com  |
| Scenic Designer: Emily Allen allene4@uw.edu |
| Costume Designer: Chante` Hamann chamann@uw.edu |
| Lighting Designer: Trevor Cushman cushmatw@uw.edu  |

Sound Designer:

Technical Director: Alex Danilchik alexd@uw.edu

Stage Manager: Alyda Sorm alyda.sorm@gmail.com

ASM:

**More Specific Design Information:**

**Costume Budget**: $3000.00

This includes all fabrics, trims, foundations, and linings for built
costumes, wigs, shoes, and shoe repair, accessories, special make up
needs, rentals, and purchased items.  Transportation costs above or
beyond budgeted allocation, shipping and return shipping, damages or
replacement on rentals also need to be considered from this budget.
Specific shop supplies are also included depending on the needs of the
production.

**First Look at Preliminary Designs: 7/11**

**Bidding Package Due: 7/16**

**Final Designs Due: 8/27**

**First Rehearsal 9/17 at 6:30pm in either Hutchinson 202 or 154**

**See Attached for more specific information**

**Costume Shop Schedule:**

Show in Shop: 9/17 to 10/12

Last Day for Notes: 10/23

Strike: 11/5

Return Borrowed Items within 5 Days of Dry Cleaning Return

**1st Technical Rehearsal: 10/13 –** The first day of tech will be an 8.5 out of 10 Saturday tech followed by 4 hour techs on Monday through Friday (all with costumes) culminating in a Preview Saturday October 20, Sunday off, Monday 4 hour Rehearsal, Tuesday Preview October 23

**Opening Night: 10/24//2018 7:30pm and the show runs through November 4, 2018**

**Advance Photos:** are taken during the rehearsal process often just before rehearsals normally featuring up to 3 actors. You will work with the constituent relations officer, currently Bobbin Ramsey, on this.

**Production Meetings:** will be scheduled weekly beginning the week 9/17 generally after 4:30pm on Wednesday or Thursday afternoons

**Show and Tell:** 10/2- 4:30pm – 6:00pm in Hutchinson 218

In concert with your fellow designers and the director, please be prepared to present concepts and visual representation of your design to a gathering of graduate students, faculty and staff.

**If** you have any questions about this information please speak to Josie Gardner 206-543-5246, jogard@uw.edu or Anne Stewart 206-543-0790 astewart@uw.edu . It is important that you meet your deadlines and are prepared with as complete a design as possible for the Shop Manager to bid. Please sign one of the copies of this letter below to indicate that you have read and understood this information and return to Anne at Box 353950.

No funds will be spent on the show prior to receiving signed letters from director and designers.

Thank you,

Anne Stewart

General Manager for Production \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Josie Gardner

Costume Shop Manager \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Chante` Hamann

Designer \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_